## Sheet1
Activity Code | Activity Description | Normal Cost (BDT) | Immediate Predecessors | Optimistic Estimate | Most Likely Estimate | Pessimistic Estimate
A | Site clearing | 18415 | - | 1 | 2 | 3
B | Foundation | 12643 | A | 2 | 3.5 | 8
C | Block Laying | 52811 | B | 6 | 9 | 18
D | Roofing | 41658 | C | 4 | 5.5 | 10
E | Plumbing | 50179 | C | 1 | 4.5 | 5
F | Electrical work | 52681 | E | 4 | 4 | 10
G | Plastering | 63894 | D | 5 | 6.5 | 11
H | Fixing up of doors and windows | 35905 | E,G | 5 | 8 | 17
I | Ceiling | 40997 | C | 3 | 7.5 | 9
J | Flooring | 42394 | F,I | 3 | 9 | 9
K | Interior Fixtures | 47643 | J | 4 | 4 | 4
L | Exterior fixtures | 33887 | J | 1 | 5.5 | 7
M | Painting | 41539 | H | 1 | 2 | 3
N | Landscaping | 36913 | K,L | 5 | 5.5 | 9